## Acceptance Criteria
Week | Phase | Acceptance Criteria | Sign-off
1 | Scope Finalization, Requirements Gathering & Environment Setup | Scope document finalized & signed.
1 | Scope Finalization, Requirements Gathering & Environment Setup | Required modules confirmed (CRM, Helpdesk, VOIP, Calendar, Invoicing, Contacts, Custom apps).
1 | Scope Finalization, Requirements Gathering & Environment Setup | Business requirements & customization list finalized (MOH integration, red invoice, referral tracking, Misa, easyHR, CloudDoctor).
1 | Scope Finalization, Requirements Gathering & Environment Setup | Vietnamese language pack installed & localization confirmed.
1 | Scope Finalization, Requirements Gathering & Environment Setup | Deliverables: Requirements confirmation document, working dev environment, demo
2 | Module Installation & Core Configuration | Core modules installed & configured: CRM , Calendar, Invoicing (multi-price lists, AR, payment recording), custom placeholders for MOH APIs, VOIP, Misa, easyHR, CloudDoctor.
2 | Module Installation & Core Configuration | Email/ mobile push notifications active.
2 | Module Installation & Core Configuration | CRM custom fields, price list filters/reporting, referral type, presenting symptoms configured.
2 | Module Installation & Core Configuration | Lead pipeline stages updated.
2 | Module Installation & Core Configuration | Lookup code lists defined (client type, city, facility type).
2 | Module Installation & Core Configuration | Staff roles created with permissions.
2 | Module Installation & Core Configuration | Deliverables: Installed modules, draft CRM configuration.
3 | Custom Development & Business Logic Configuration | Referral/lead source tracking functional.
3 | Custom Development & Business Logic Configuration | Auto-generation of Client IDs implemented.
3 | Custom Development & Business Logic Configuration | Lead-to-contact-to-booking process operational.
3 | Custom Development & Business Logic Configuration | Booking/service delivery/invoicing/AR workflows configured (visit location, service type, clinician assignment, etc.).
3 | Custom Development & Business Logic Configuration | Calendar booking visualization customized.
3 | Custom Development & Business Logic Configuration | EasyHR push notification integration started.
3 | Custom Development & Business Logic Configuration | VOIP integration started, call logging functional.
3 | Custom Development & Business Logic Configuration | Deliverables: Draft CRM & Booking modules.
4 | Continued Development, Internal QA & Data Import | Week 3 development finalized.
4 | Continued Development, Internal QA & Data Import | End-to-end workflow tested internally: Lead → Contact → Booking → Assignment → Clinical Notes → MOH Submission (2-part) → Invoicing → Treasury submission.
4 | Continued Development, Internal QA & Data Import | MOH mandatory fields enforced.
4 | Continued Development, Internal QA & Data Import | Lookup codes, sample data imported.
4 | Continued Development, Internal QA & Data Import | Internal testing complete; bugs fixed.
4 | Continued Development, Internal QA & Data Import | Deliverables: Demo
5 | UAT Preparation & Kick-Off | UAT environment set up (matches staging config).
5 | UAT Preparation & Kick-Off | UAT roles setup for Sales/Admin, Operations, Nurses/Doctors, Finance.
5 | UAT Preparation & Kick-Off | UAT walkthrough with stakeholders complete.
5 | UAT Preparation & Kick-Off | UAT testing started with live-like data.
5 | UAT Preparation & Kick-Off | Deliverables: Demo to staff
6 | UAT Completion, Final Adjustments, Pre-Go-Live | UAT completed; critical bugs resolved.
6 | UAT Completion, Final Adjustments, Pre-Go-Live | Validation of: Red invoice logic, client source reporting & MOH compliance, role-based permissions.
6 | UAT Completion, Final Adjustments, Pre-Go-Live | Final data migration from legacy CRM (clients, staff, activity history, workflows).
6 | UAT Completion, Final Adjustments, Pre-Go-Live | Deliverables: UAT signoff
7 | User Training | Role-based training delivered.
7 | User Training | Quick guides & optional videos provided.
7 | User Training | Q&A and simulation sessions completed.
7 | User Training | Deliverables: Signed attendance, training materials archive.
8 | Go Live & Post-Go-Live Support (Hypercare) | Production system deployed & integrations active.
8 | Go Live & Post-Go-Live Support (Hypercare) | First-week bookings, assignments, invoices monitored.
8 | Go Live & Post-Go-Live Support (Hypercare) | Support channel operational; daily stand-ups conducted.
8 | Go Live & Post-Go-Live Support (Hypercare) | Monthly reporting automation in place.
8 | Go Live & Post-Go-Live Support (Hypercare) | Deliverables: Known issues tracker
| Performance of system | ????