## Rvk_req_table
Screen/Functionality | Requirement | Completion Status
General Notes | Flow Dashboard menu name should change to Home Page | Complete
General Notes | Show user name and designated place of work (province) at the top of the screen . To do that, you will have to add a many2one filed for hr.location in user From view. Below access_role_id in base.view_users_form | Complete
General Notes | Collect province as soon as possible, preferably in the initial contact form | TBD
General Notes | Language option must translate all items; provide a copy of the language table | TBD
General Notes | Every screen shows the current back-to-home button . Show a icon of Home and should take to Home page / Flow Dashboard | Complete
General Notes | Wherever the client name appears, show the Client ID | TBD
General Notes | All List views should be wide enough to show complete column hedaings. | Complete
General Notes | Show sub-menu items as a horizontal strip at the top of the screen | Complete
General Notes | Add another icon at the topmost bar near the Notifications for new bookings and future bookings, cancellations, rescheduling with different icons on the left; clicking an item opens the booking and removes it from the notification list | Complete
General Notes | Province is a separate field related to the facility for screening users and selecting facilities | TBD
General Notes | Address field can be used for facilities and individuals; use a popup to show compound address fields, save individual fields, and only display via popup when first entered or edited | Complete
Main Client Menu - Client information | Add province (to filter users) | Complete
Main Client Menu - Client information | Add a title field for the name | Complete
Main Client Menu - Client information | Add deceased flag: default false; can be set to true automatically or manually | Complete
Main Client Menu - Client information | Add health insurance card number | Complete
Main Client Menu - Client information | Add occupation | Complete
Main Client Menu - Client information | Add ethnicity | Complete
Main Client Menu - Client information | Deceased flag display: blank with no label if false; international symbol if true | Complete
Main Client Menu - Client information | Store date/time and reporter details in file but do not show on form | Complete
Main Client Menu - Client information | Add contact person to contact details (self or name of person); phone number is the contact person's phone | TBD
Main Client Menu - Client information | Medical information is not required here | Complete
Relationships | Add a related person without reference to a client (e.g., 3rd party payers, new referrers who have not referred yet, other individuals) | TBD
Relationships - Add Caregiver | Address | Complete
Relationships - Add Caregiver | Telephone number | Complete
Relationships - Add Payer | Address | Complete
Relationships - Add Payer | Telephone number | Complete
Relationships - Add Payer | Tax Number | Complete
Relationships - Add Payer | Legal Name for Invoice | Complete
Relationships - Add Payer | Payer ID | Complete
Relationships - Add Payer | Bank Name | Complete
Relationships - Add Payer | Account Number | Complete
Relationships - Add Referrer | Address | Complete
Relationships - Add Referrer | Telephone number | Complete
Relationships - Add Referrer | Tax Number | Complete
Relationships - Add Referrer | Legal Name for Invoice | Complete
Relationships - Add Referrer | Referrer ID | Complete
Relationships - Add Referrer | Contract Number | Complete
Relationships - Add Referrer | Referral Commission | Complete
Relationships - Add Referrer | Bank Name | Complete
Relationships - Add Referrer | Account Number | Complete
Relationships - Add Referrer | Tax Number | Complete
Relationships - Add Emergency Contact | Telephone number | Complete
Relationships - Add Emergency Contact | Alternative telephone number | Complete
Relationships - Add Emergency Contact | Availability notes | Complete
Relationships - Add Legal Guardians | Telephone number | Complete
Relationships - Add Legal Guardians | Alternative telephone number | Complete
Relationships - Add Legal Guardians | Availability notes | Complete
Relationships - Add Client Representatives | Telephone number | Complete
Relationships - Add Client Representatives | Alternative telephone number | Complete
Relationships - Add Client Representatives | Availability notes | Complete
Map | Rename Vietnamese Address to Home Address | TBD
Map | Change order of address components (see below) | TBD
Map | Add GPS coordinates | TBD
Map | Add one-way road distance from facility | TBD
Bookings | Follow the booking process as described in the word document | TBD
Bookings | Ask OMs what nurses need in booking notes | TBD
Client details menus | Provide an option to assign an unassigned booking | TBD
Dashboard - Financials | Show total number of bookings by location type and total; total paid, total unpaid, and total all bookings | TBD
Dashboard - Financials | Show amount due by days aged for each invoice | TBD
Packages | Select only; generate package in finance menu | TBD
Main CRM Menu | Rename Main CRM Menu to Sales & CRM | TBD
CRM Sub-menus - Contacts | On selection, open popup to enter initial contact data: name, contact ID, new/repeat flag, province, phone/email, and mode of contact (phone, chatbox, email, province) | TBD
CRM Sub-menus - Contacts | Provide selection box to choose existing clients/contacts | TBD
CRM Sub-menus - Contacts | System checks existing contact using name and phone/email | TBD
CRM Sub-menus - Contacts | System auto-checks source and adds ID if relevant | TBD
CRM Sub-menus - Contacts | If existing, auto-enter contact ID; if not, assign new contact ID and flag new/repeat | TBD
CRM Sub-menus - Contacts | Provide option buttons: next or home page | TBD
CRM Sub-menus - Contacts | If back to home is selected, record entry as false/junk contact | TBD
CRM Sub-menus - Contacts | If next is selected, close popup and open expanded Contact Details form | TBD
CRM Sub-menus - Follow-up activities | When selected from Home Page, open new window with menu items on top and search box for client/alternative client | TBD
CRM Sub-menus - Follow-up activities | When selected from Contact Details form, retain current contact details as current client | TBD
CRM Sub-menus - Follow-up activities | Log as Lead (in calendar) | TBD
CRM Sub-menus - Follow-up activities | Log planned activity (in calendar) | TBD
CRM Sub-menus - Follow-up activities | Show all current leads sorted by planned follow-up date; selection opens lead follow-up form | TBD
CRM Sub-menus - Follow-up activities | If follow-up results in booking, show new booking form | TBD
CRM Sub-menus - Follow-up activities | If follow-up results in no booking, show booking lost form | TBD
CRM Sub-menus - Follow-up activities | Show all current planned activities sorted by planned follow-up date; selection opens activity follow-up form | TBD
CRM Sub-menus - Follow-up activities | Show calendar of current leads and activities; selection opens lead or activity follow-up form | TBD
CRM Sub-menus - Follow-up activities | Recent client follow-up: show recent clients with selected service; selection shows client and last visit(s); log in lead calendar to follow up now or later; outcome is new booking or rejection | TBD
CRM Sub-menus - Follow-up activities | Visit satisfaction follow-up: show recent clients without follow-up phone calls (placeholder for now) | TBD
Contact Details form | Show this part of the form only if the contact is not terminated at the initial contact stage | TBD
Contact Details form | Display initial contact details: name, ID, phone/email, mode of contact (phone/zalo/facebook/website/email), new/repeat, province; add address field and tag field to add type of related person option | TBD
Contact Details form | Collect reason for contact | TBD
Contact Details form | Collect contacting on behalf of (self/another person) | TBD
Contact Details form | Collect name of other person (select from client list or enter new client name) | TBD
Contact Details form | Horizontal menu on top | TBD
Contact Details form | Home page option: selecting it records the call as junk call and returns to home page | TBD
Contact Details form | Booking option: open new window with booking menus; also available from Bookings and Assignments main menu | TBD
Booking menu - Client Details | Complete or view client details for a new contact; autofill if contacting person is the client or a repeat client; include controls to add services or go back to booking page | TBD
Booking menu - Service Requirements | Collect services and sub-categories; add operations details or back-to-booking controls | TBD
Booking menu - Service Requirements | Add commission fields: Commission Due To, % commission, commission payment duration | TBD
Booking menu - Booking Details | Create initial booking: date/time on calendar; include assign booking and back-to-booking controls | TBD
Booking menu - Assign Booking | Not compulsory; Sales can assign nurse; include finished button to return to booking page | TBD
Booking menu - Assign Booking | Add service fee field in VND for OM-negotiated casual provider fee; finished returns to prior screen | TBD
Booking menu - Cancellation | Show cancellation form | TBD
Booking menu - Cancellation | Capture date/time stamp | TBD
Booking menu - Cancellation | Capture reason for cancellation | TBD
Booking menu - Cancellation | Capture who cancelled (client side) | TBD
Booking menu - Cancellation | Capture who reported cancellation (name/position) | TBD
Booking menu - Cancellation | If not a new client first visit, capture who last visited this client | TBD
Booking menu - Reschedule | Show booking calendar | TBD
Booking menu - Telemedicine | Refer to Duty Doctor with details; notify doctor and make details available | TBD
Booking menu - Consultation | Transfer for consultation to Duty Doctor, Head Nurse, or OM | TBD
Booking menu - Escalate Contact | Transfer contact for further processing to Head Nurse or OM (not the same as consultation) | TBD
Booking menu - Actions | Send message option | TBD
Booking menu - Actions | Log as Lead | TBD
Booking menu - Actions | Log Activity | TBD
Booking menu - Actions | Log Note | TBD
Booking menu - Actions | On closing Booking menu, post new booking/reschedule/cancellation to New Bookings log and notify OM | TBD
Contact status | Contact status field values: Active, Booking, Lead, Lost Booking, Spam Call | TBD
Contact status | If junk call, tag caller name/phone number as Spam Caller (change if new call results in booking, lead, or lost booking) | TBD
Bookings Menu | Rename to Bookings and Assignments; display content as above | TBD